## Project Plan - CS4
Task Number | Task name/Title | Assigned to | Planned Start | Planned end | Deadline for Task | Group Meeting Time
1 | rsearch for main layout | Everyone | 2022-12-07 | 2022-12-10
1.1 | Online search on user requests | Sameer, Ijtihad and saif
1.2 | Rsearch on html tags needed | Qays
1.3 | CSS research | Adnan
1.4 | Javascript research | Adnan |  |  |  | 2022-12-11
2 | Color and graphics | Adnan,Sameer | 2022-12-14 | 2022-12-15
2.1 | Color and graphics | Adnan,Sameer
3 | Content presentation | Saif and Qays | 2022-12-14 | 2022-12-15
3.1 | Common fonts | Saif and Qays
3.2 | Font sizes font colors | Qays
4 | Functionality |  | 2022-12-16 | 2022-12-17
4.1 | External hyperlinks | Adnan
4.2 | Javascript(e.g buttons) | Ijtihad
4.3 | Timer design-CSS | Obaid
4.4 | Timer function-Javascript | Obaid
4.5 | Responivity | Adnan |  |  |  | 2022-12-18
5 | Prototype 1 |  | 2022-12-19 | 2022-12-23
5.1 | Prototype 1 | All of us
6 | Prototype 2 |  | 2022-12-26 | 2022-12-30 |  | 2022-12-30
6.1 | Prototype 2 | All of us
7 | Prototype 3 |  | 2022-12-31 | 2023-01-03
7.1 | Prototype 3 | All of us
8 | user testing | Sameer,Saif | 2023-01-03 | 2023-01-04
8.1 | Tests | Sameer
8.2 | Note taking | Saif
9 | Acessibility |  | 2023-01-03 | 2023-01-04
9.1 | Acessibility | Adnan |  |  |  | 2022-01-04
10 | Finalizing product | All of us | 2023-01-05 | 2023-01-11
10.1 | Bug report | Adnan
10.2 | Test tables | Saif
10.3 | Design checks | Obaid
10.4 | HTML checks | Ijtihad
10.5 | CSS checks | Qays
10.6 | Javascript checks | Sameer
10.7 | Page 1 check | Ijtihad
10.8 | Page 2 check | Qays
10.9 | Time management tool Check | Adnan
2022-01-11